## Intro
FY2015 Budget Application Instructions
From the President & CFO - This year the company has made a strategic investment in a world-class collaborative planning application. In partnership with IBM, the global leader in Performance Management and our hard working Financial Systems project implementation team, we are excited to introduce the new IBM Cognos Performance Management application.
Our system is designed to improve the accuracy and timeliness of our planning process while providing our user community with the tools necessary to analyze past performance and more confidently plan for the future. Our goal is to get this done while at the same time improving the quality of life of our business planners.
Process Schedule |  |  |  | Contacts
Date |  | Activity |  | Name | Extension
10/12/2015 |  | Kick Off |  | Will Roberts, CFO | x5876
10/14/2015 |  | Planning Application Open |  | Steve Adams, FPA Manager | x4424
10/29/2015 |  | First Pass Review |  | Jill Warren, FPA Analyst | x3424
11/5/2015 |  | Revised Guidelines Published
11/12/2015 |  | Second Pass Review |  | To Start, Click here;
11/17/2015 |  | Department Presentations
11/21/2015 |  | Final Plan Published
Version : |  | 4.5

## Tasks
|  |  | CUBE: | region06:Task Workflow
|  |  | organization | Massachusetts | 2015
FY2015 Budget Application Instructions
| Days Left | Overdue |  | Task | Launch | Status | Due Date | Commentary
All Tasks | 0 |  |  | All Tasks |  | In Progress
1 | 0 |  |  | Revenue |  | In Progress
2 | -1734 |  |  | Enter New Products |  | Complete | 2013-08-08 | Price increase in 4G product line to boost Margin
3 | -1734 | Overdue |  | Plan Units Sold |  | Not Started | 2013-08-08
5 | 0 |  |  | Headcount |  | Complete
7 | -1605 |  |  | Amend Existing / Add new Headcount |  | Complete | 2013-12-15
8 | -1605 |  |  | Review Total Compensation Spend |  | Complete | 2013-12-15
9 | 0 |  |  | Capital |  | Not Started
10 | -1605 | Overdue |  | Add New Capital Requests |  | Not Started | 2013-12-15
11 | -1605 | Overdue |  | Review IS and BS Impact |  | Not Started | 2013-12-15
12 | 0 |  |  | OPEX |  | Complete
13 | -1605 |  |  | Plan Marketing expense |  | Complete | 2013-12-15
14 | -1605 |  |  | Plan Phased costs |  | Complete | 2013-12-15
15 | 0 |  |  | Income Statement |  | In Progress
16 | -1605 |  |  | Review Allocations |  | Complete | 2013-12-15
17 | -1605 | Overdue |  | Update Forecast |  | Not Started | 2013-12-15
18 | -1605 | Overdue |  | Review Exchange Differences |  | Not Started | 2013-12-15
19 | -1605 |  |  | Review Final P&L |  | Complete | 2013-12-15

## Status
FY Plan Progress
Task Status |  | Metrics Status
region06:Task Workflow |  |  | region06:incomeStatement | region06:incomeStatement | region06:incomeStatement
Massachusetts |  |  | Local | Local | Local
|  |  | y2 | y2 | y2
|  |  | 2015 | 2015 | 2015
|  |  | Year | Year | Year
|  |  | Target | Budget | Variance
Tasks Completed | 7 |  | Target 2015 | Budget 2015 | Variance
Tasks Remaining | 5 | Gross Margin | 1781439.6657 | 5697532.5353 | 3916092.8696 | 0
|  | 6099 PAYROLL | 710411.918 | 645575.9269 | 64835.9911 | 0
|  | 6499 MARKETING | 99851.304 | 141614.8 | -41763.496 | 1
|  | 6599 DEPRECIATION | 134270.0626 | 1455500 | -1321229.9374 | 1
|  | Net Profit | 187716.6191 | 3022619.0484 | 2834902.4293 | 0
|  | # Incomplete Metrics | 2

## {PL}PickLst (hidden)
Complete
Not Started